## Overview
Overall Task | Priority | Data Finished
Data Collection | Very High | 2023-10-23
Content-Based Filtering Recomender | High
Collaborative Filtering Recommender | Medium
Hybrid Recommender System | Low
Evaluate the recommenders using multiple datasets | Medium
Web Interface | Very Low

## Data Collection
Sub-Task | Priority | Finished? | Date Finished
Create a python script that collects anime data from MyAnimeList | High | Yes | 2023-09-30
Create a script that collects username data | High | Yes | 2023-09-30
Create a script that collects user anime lists using the username data | High | Yes | 2023-09-30
Generate data using the scripts and convert the data to CSV files | High | Yes | 2023-09-30
Explore the CSV files and see if there will be enough useful data | Medium | Yes | 2023-10-23

## Content-Based Filtering
Sub-Task | Priority | Completed? | Completion Date
Update the test recommendations function to work with the new evaluation method | Medium | Yes | 2024-02-15
Create graphs for evaluating the system when making 10, 20, and 30 recommendations | Medium | Yes | 2024-02-15
Add the ability to make mass recommendations without evaluating | Low | Yes | 2024-02-15
Change evaluation metric to work per user (i.e. for the predictions made for that user) | Medium | Yes | 2024-01-15
Create an initial custom evaluation metric that uses minimum distance | Medium | Yes | 2024-01-13
Create graphs using the evaluation metric | Medium | Yes | 2024-01-13
Switch the CBF recommender to support multiple distance metrics e.g. cosine distance, euclidean distance | Medium | Yes | 2024-01-02
Add a function that can vectorise anime using TF-IDF | High | Yes | 2023-11-13
Create a basic content-based filtering recommender using cosine similarity | High | Yes | 2023-11-13
Improve the vectorisation of anime | Low | No
Support cross validation for the CBF model | Low | No
Fix any remaining issues with the recommender | Medium | No

## Collaborative Filtering
Sub-Task | Priority | Finished? | Date Finished
Setup the dataset to work with Scikit Surprise | High | Yes | 2024-01-22
Create the SVD++ model and fit it with the dataset | High | Yes | 2024-02-22
Remove shows that have not been finished, or have been dropped. | Low | No
Normalise the user ratings per user | Low | No
Make predictions using the model | High | Yes | 2024-01-28
Get the predictions to work with my minimum distance evaluation | Medium | Yes | 2024-01-29
Switch to use SVD | High | Yes | 2024-01-30
Compare different algorithms e.g. SVD, SVD++ etc. | Medium | No
Create a graph that looks like the CBF evaluation graph | Medium | No
Perform a GridSearch to hypertune the algorithm parameters for the final model | Low | No

## Multiple Datasets Evaluation
Sub-Task | Priority | Finished? | Date Finished
Rename the existing user ratings dataset as the standard set | Medium | No
Add the new users dataset | High | No
Evaluate each recommender on the new users dataset | High | No
Create graphs comparing the performance on both datasets | Medium | No
Remove watching and dropped shows from both datasets | Medium | No

## Web Interface
Sub-Task | Priority | Finished? | Date Finished