## Overview
Overall Task | Priority | Data Finished
Data Collection | Very High | 2023-10-23
Content-Based Filtering Recomender | High | 2024-03-15
Collaborative Filtering Recommender | Medium
Hybrid Recommender System | Low
Evaluate the recommenders using multiple datasets | Medium | 2024-03-15
Web Interface | Very Low | 2024-03-16

## Data Collection
Sub-Task | Priority | Finished? | Date Finished
Create a python script that collects anime data from MyAnimeList | High | Yes | 2023-09-30
Create a script that collects username data | High | Yes | 2023-09-30
Create a script that collects user anime lists using the username data | High | Yes | 2023-09-30
Generate data using the scripts and convert the data to CSV files | High | Yes | 2023-09-30
Explore the CSV files and see if there will be enough useful data | Medium | Yes | 2023-10-23

## Content-Based Filtering
Sub-Task | Priority | Completed? | Completion Date
Update the test recommendations function to work with the new evaluation method | Medium | Yes | 2024-02-15
Create graphs for evaluating the system when making 10, 20, and 30 recommendations | Medium | Yes | 2024-02-15
Add the ability to make mass recommendations without evaluating | Low | Yes | 2024-02-15
Change evaluation metric to work per user (i.e. for the predictions made for that user) | Medium | Yes | 2024-01-15
Create an initial custom evaluation metric that uses minimum distance | Medium | Yes | 2024-01-13
Create graphs using the evaluation metric | Medium | Yes | 2024-01-13
Switch the CBF recommender to support multiple distance metrics e.g. cosine distance, euclidean distance | Medium | Yes | 2024-01-02
Add a function that can vectorise anime using TF-IDF | High | Yes | 2023-11-13
Create a basic content-based filtering recommender using cosine similarity | High | Yes | 2023-11-13
Fix any remaining bugs | Medium | Yes | 2024-03-15

## Collaborative Filtering
Sub-Task | Priority | Finished? | Date Finished
Setup the dataset to work with Scikit Surprise | High | Yes | 2024-01-22
Create the SVD++ model and fit it with the dataset | High | Yes | 2024-02-22
Remove shows that have not been finished, or have been dropped. | Low | Yes | 2024-02-17
Make predictions using the model | High | Yes | 2024-01-28
Get the predictions to work with my minimum distance evaluation | Medium | Yes | 2024-01-29
Switch to use SVD | High | Yes | 2024-01-30
Compare different algorithms e.g. SVD, SVD++ etc. | Medium | Yes | 2024-02-10
Create a graph that looks like the CBF evaluation graph | Medium | Yes | 2024-02-10
Perform a GridSearch to hypertune the algorithm parameters for the final model | Low | No

## Hybrid System
Sub-Task | Priority | Finished? | Date Finished

## Multiple Datasets Evaluation
Sub-Task | Priority | Finished? | Date Finished
Add the new users dataset | High | Yes | 2024-02-17
Evaluate each recommender on the new users dataset | High | Yes | 2024-02-19
Create graphs comparing the performance on both datasets | High | Yes | 2024-03-15
Remove watching and dropped shows from both datasets | Medium | Yes | 2024-02-17
Remove new users from the standard dataset | Medium | Yes | 2024-02-17

## Web Interface
Sub-Task | Priority | Finished? | Date Finished
Show the recommendations for a specific user | High | Yes | 2024-03-06
Allow the recommender to be chosen | High | Yes
Allow a random user to be chosen | Medium | Yes | 2024-03-06
Allow a specific user to be chosen | High | Yes | 2024-03-06
Allow the number of recommendations to be chosen | Medium | Yes | 2024-03-06
Remove the distance column from the recommendations table | Low | Yes | 2024-03-06
Fix Collaborative Recommenders so they show their recommendations results | High | Yes | 2024-03-16
Add a second page showing the evaluation results | High | Yes | 2024-03-16