## Overview
Overall Task | Priority | Data Finished
Data Collection | Very High | 2023-10-23
Content-Based Filtering Recomender | High
Collaborative Filtering Recommender | Medium
Hybrid Recommender System | Low
Evaluate the systems for new users | Low
Web Interface | Very Low

## Data Collection
Sub-Task | Priority | Finished? | Date Finished
Create a python script that collects anime data from MyAnimeList | High | Yes | 2023-09-30
Create a script that collects username data | High | Yes | 2023-09-30
Create a script that collects user anime lists using the username data | High | Yes | 2023-09-30
Generate data using the scripts and convert the data to CSV files | High | Yes | 2023-09-30
Explore the CSV files and see if there will be enough useful data | Medium | Yes | 2023-10-23

## Content-Based Filtering
Sub-Task | Priority | Finished? | Date Finished
Add a function that can vectorise anime using TF-IDF | High | Yes | 2023-11-13
Create a basic content-based filtering recommender using cosine similarity | High | Yes | 2023-11-13
Support RMSE for evaluating the CBF recommender | Medium | Yes | 2023-11-13
Switch the CBF recommender to support multiple distance metrics e.g. cosine distance, euclidean distance | Medium | Yes | 2024-01-02
Add a custom evaluation metric that uses minimum distance | Medium | Yes | 2024-01-13
Create graphs using the evaluation metric(s) | Medium | Yes | 2024-01-13
Improve the vectorisation of the anime | Low | No

## Collaborative Filtering
Sub-Task | Priority | Finished? | Date Finished

## New Users Evaluation
Sub-Task | Priority | Finished? | Date Finished

## Web Interface
Sub-Task | Priority | Finished? | Date Finished